## BugReport
Status Overview |  |  | Priority Overview
Open | 5 |  | Critical | 1
Reopen | 0 |  | High | 3
Suggestion | 0 |  | Medium | 0
Need details | 0 |  | Low | 1
Fix | 0
Close | 0
Not a bug | 0
Next Version | 0
Total Pending | 5
Bug ID | Linked Test Case ID | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Status | Priority | Reported By | Assigned To
BUG-001 | TC-LOGIN-004 | Login allows blank username | 1. Open login page 2. Leave username blank 3. Enter valid password 4. Click Login | System should reject login when username is blank and display error message. | System accepts login attempt without username. | High | Open | Critical | Khadija | Dev1
BUG-002 | TC-ADDUSER-001 | No character limit on username | 1. Open "Add New Employee" page 2. Add employee with 300 char name 3. Click Submit | System should apply a character limit and display error message. | System UI breaks when long string is entered | Medium | Open | High | Khadija | Dev2
BUG-003 | TC-LOGIN-002 | Login allows inavlid email string format | 1. Open login page 2. Enter invalid email 3. Enter valid password 4. Click Login | System should reject login when email is invalif and display error message. | System accepts login attempt when invalid email is entered | High | Open | High | Khadija | Dev1
BUG-004 | TC-FILE-001 | File upload accepts .exe files without validation | 1. Navigate to the File Upload section. 2. Click “Choose File” and select an .exe file (e.g., test.exe). 3. Click Upload. | The system should reject unsupported file types (e.g., .exe) and display a validation error message. | The system accepts and “uploads” the .exe file without any validation or warning. | Medium | Open | Low | Khadija | Dev3
BUG-005 | TC-LOGIN-006 | No account lockout after multiple failed login attempts | . Navigate to the login page. 2. Enter a valid username and an invalid password. 3. Repeat step 2 three or more times consecutively. 4. Observe system behavior. | After 3–5 failed attempts, the system should either: • Lock the account temporarily (e.g., 15 mins), OR • Display a warning/captcha to prevent brute-force attempts. | The system allows unlimited failed login attempts without restriction or warning. | High | Open | High | Khadija | Dev1

## Legend
Status
Open → Bug is newly reported and not yet fixed.
Reopen → Bug was marked as fixed/closed but reappeared.
Suggestion → Enhancement request, not a defect.
Need details → Report is incomplete and needs clarification.
Fix → Developer has fixed the bug (awaiting testing).
Close → Bug is verified as fixed and officially closed.
Not a bug → Reported issue is not a valid defect.
Next Version → Bug deferred to a future release.
Priority
Critical → Must be fixed immediately; blocks release/testing.
High → Important issue; should be fixed in the current release.
Medium → Fix is needed but can wait until higher priorities are resolved.
Low → Minor issue; cosmetic or low impact, can be fixed later.
Severity
High → Severe impact; system crash, data loss, or major functionality broken.
Medium → Noticeable impact; some functions don’t work correctly, but workarounds exist.
Low → Minor issue; cosmetic/UI defect or small inconvenience.